QUANTRO SOFTWARE LABS

QuantroApex

Development Plan & Sprint Structure

Agile / Scrum  ·  Solo Build  ·  AI-Assisted Development

MVP Phase  ·  10 Sprints  ·  11 Weeks

Development Blueprint  —  Version 3.0

Confidential — Internal Document

2026

# Table of Contents

# 1. Development Methodology

## 1.1 Chosen Model — Agile (Scrum), Solo Build

QuantroApex is built using Agile Scrum by a single technical founder, assisted by an AI coding agent. This combination replaces what would traditionally require a team of four to five developers while maintaining the discipline and quality a financial product demands.

Why this works for QuantroApex:

1. The founder owns the full stack — Flutter, Node.js, PostgreSQL — all MVP technologies

2. AI coding agents handle boilerplate, scaffolding, repetitive patterns, and test generation

3. Sprint structure provides discipline and prevents scope creep in a solo environment

4. Detailed product blueprint and design system give the AI agent precise context every time

5. Timeline compresses from a traditional 20 weeks to approximately 11 weeks

## 1.2 The AI Coding Agent — Role & Boundaries

| AI Agent Handles Well | Founder Must Own |
| --- | --- |
| Project scaffolding and boilerplate | All architecture decisions |
| API endpoint generation from specs | Execution engine and risk enforcement logic |
| Flutter screen builds from design system | Security review — auth and data isolation |
| Database schema from documented models | AI/ML layer design and direction in V2 |
| Unit and integration test writing | Product judgment — what gets built and why |
| UI implementation from design tokens | Design system definition and consistency audit |
| Documentation generation | Financial logic correctness — always verify |

## 1.3 Scrum in a Solo Context

| Ceremony | Solo Adaptation | Frequency |
| --- | --- | --- |
| Sprint Planning | Founder sets sprint goal and task list in writing | Start of each sprint |
| Daily Standup | Written daily log — done, doing, blockers. 5 minutes. | Daily |
| Sprint Review | Demo to self against exit criteria. Record what shipped. | End of each sprint |
| Sprint Retrospective | Written reflection — what slowed me, what to improve | End of each sprint |
| Backlog Refinement | Re-prioritise upcoming work mid-sprint | Mid-sprint, 30 minutes |

## 1.4 Sprint Cadence

- Sprint duration: 1 week

- Sprint 0: 2 to 3 days — setup only

- Sprints 1 to 10: 1 week each

- Total MVP duration: approximately 11 weeks to beta launch

- Sprint 10 exception: 2 weeks — testing and polish cannot be compressed on a financial product

## 1.5 Definition of Done

- Feature works end-to-end on staging environment

- AI agent output reviewed and validated against the product blueprint

- Design system tokens verified — no visual inconsistencies introduced

- Unit tests written and passing

- Financial logic double-checked manually by the founder

- Deployed to staging via CI/CD pipeline

# 2. Build Team

## 2.1 Team Structure

| Role | Type | Responsibility |
| --- | --- | --- |
| Founder — Product, Architecture & Dev | Full-time | Product direction, all architecture decisions, full development with AI agent, design system ownership, security and financial logic review |
| AI Coding Agent | Tool | Scaffolding, screen builds from design tokens, endpoint generation, test writing, debugging support, UI implementation |

No external hires are required for the MVP. The founder and AI coding agent are the complete build team. The design system — defined in Sprint 0 — is the mechanism that replaces a dedicated UI/UX designer.

## 2.2 V2 Hiring — When to Start Looking

The AI/ML Engineer is the most critical V2 hire and the hardest to find. The search begins during MVP Sprint 6 — not after beta launch.

| Role | When to Hire | Why Then |
| --- | --- | --- |
| AI/ML Engineer (Python, RL) | Begin search Sprint 6 — hire before V2 planning | Rarest skill in the stack. Long search time. Must join V2 planning from the start. |
| Data Engineer | Begin search Sprint 8 — hire at V2 start | Kafka and TimescaleDB architecture needs this role before AI training begins |
| Backend Developer | V3 planning phase | Multi-broker integrations significantly grow API complexity |
| QA Engineer | V2 start | AI outputs require dedicated testing beyond solo review |

# 3. Design Approach — AI-Assisted, System-Driven

## 3.1 The Core Principle

Without a dedicated designer, consistency becomes the founder's responsibility and the design system becomes the tool that enforces it. An AI agent building screens one by one will drift — spacing varies, component styles diverge, tone shifts. A single, well-defined design system document prevents this entirely.

The rule: every screen the AI agent builds references the design system first.

Same tokens. Same components. Same rules. Every time. No exceptions.

## 3.2 Step 1 — Define the Design System in Sprint 0

Before any screen is built, the founder creates a Design System Document. This is the single source of truth the AI agent references on every UI task. It lives in the repository alongside the code.

### Colour System

Define every colour as a named token — not a raw hex value in the code. The agent uses token names, not hex codes. This makes global changes a one-line edit.

| Token Name | Hex Value | Usage |
| --- | --- | --- |
| colorPrimary | #0A1628 | Primary text, headers, key UI elements |
| colorAccent | #1B4FD8 | Action buttons, active states, highlights |
| colorAccentMid | #2563EB | Secondary interactive elements |
| colorSurface | #F0F6FF | Card backgrounds, info boxes |
| colorBorder | #E2E8F0 | Dividers, input borders, table lines |
| colorMuted | #64748B | Secondary text, timestamps, labels |
| colorSuccess | #16A34A | Positive outcomes, profit indicators |
| colorWarning | #D97706 | Threshold alerts, caution states |
| colorDanger | #DC2626 | Loss indicators, emergency states — used sparingly |
| colorWhite | #FFFFFF | Screen backgrounds, card surfaces |

colorDanger is used with restraint. Quiet Confidence means the interface stays composed even when results are negative. A red number communicates loss — a red banner with alerts does not.

### Typography Scale

One font family throughout — clean, readable, no decorative fonts on a financial product.

| Token Name | Size | Usage |
| --- | --- | --- |
| textDisplay | 32sp | Portfolio value on dashboard — the hero number |
| textH1 | 24sp | Screen titles |
| textH2 | 20sp | Section headers, card titles |
| textH3 | 18sp | Sub-section labels |
| textBody | 16sp | Primary body text, descriptions |
| textSecondary | 14sp | Supporting text, metadata, timestamps |
| textCaption | 12sp | Fine print, disclaimers, tooltips |

- Font weight: Regular (400) for body, Semi-bold (600) for labels, Bold (700) for display and H1 only

- Line height: 1.5x font size for body text, 1.2x for headings

- Letter spacing: Default for body, +0.5px for labels and captions

### Spacing Scale

A consistent 8-point grid. All spacing values are multiples of 8. The agent never uses arbitrary pixel values.

| Token | Value | Usage |
| --- | --- | --- |
| space1 | 4px | Micro gaps — icon to label, badge padding |
| space2 | 8px | Tight spacing — within components |
| space3 | 16px | Standard component padding |
| space4 | 24px | Section spacing, card padding |
| space5 | 32px | Large section gaps |
| space6 | 48px | Screen-level breathing room, top/bottom margins |

### Component Library — Core Components

These components are defined once in Sprint 0 and reused throughout. The agent never rebuilds a component from scratch — it uses the library.

- PrimaryButton — accent background, white text, 12px radius, 48px height, subtle shadow

- SecondaryButton — transparent background, accent border, accent text, same dimensions

- GhostButton — no border, muted text — for low-emphasis actions

- InputField — white background, colorBorder border, 12px radius, 48px height, textBody size

- Card — white background, colorBorder border, 12px radius, space4 padding, subtle shadow

- ActivityFeedEntry — Card variant, left accent bar, asset badge, plain-English text, timestamp

- StrategyCard — Card variant, risk badge, asset class chip, sparkline area, user count

- MetricTile — label in textCaption colorMuted, value in textH2 colorPrimary

- StatusBadge — small pill, coloured background matching status, textCaption white text

- SectionHeader — textH2 colorPrimary, optional right-side action link in textSecondary accent

- BottomSheet — white surface, drag handle, space4 padding, used for strategy detail and trade detail

### Iconography

- Icon library: Material Symbols — consistent, well-maintained, free

- Icon size: 20px for inline, 24px for navigation, 32px for feature icons

- Icon colour: always matches the text it accompanies — never standalone accent colour icons

- Never use decorative or illustrative icons — this is a precision financial product

### Motion & Animation

Quiet Confidence means motion is functional, not decorative.

- Screen transitions: 200ms fade — nothing slides dramatically

- Bottom sheet open: 250ms ease-out — smooth, not bouncy

- Data updates on activity feed: fade-in 150ms — new entries appear, not fly in

- Button press: 100ms opacity reduction — tactile feedback, not animation

- No looping animations, no celebratory motion, no attention-seeking transitions

## 3.3 Step 2 — Define Screen Specs Before Building

Before the agent builds any screen, the founder writes a plain-English screen spec. This takes 10 to 15 minutes per screen and dramatically improves the quality of the agent's output. The spec follows a consistent format.

Screen Spec Format:

Screen name and purpose — one sentence

Layout structure — how the screen is organised top to bottom

Components used — reference component library names exactly

Data displayed — what API data populates each element

Interactions — what taps, swipes, or inputs exist

States — empty state, loading state, error state

Quiet Confidence notes — any specific tone or restraint requirements for this screen

Example spec for the Home Dashboard:

Home Dashboard Screen Spec

Purpose: The first screen users see. Communicates portfolio status and Apex state with maximum calm.

Layout (top to bottom):

1. Greeting line — "Good morning, [name]" in textSecondary colorMuted

2. Portfolio value — textDisplay colorPrimary, bold, centred

3. Today's movement — textBody, colorSuccess if positive, colorDanger if negative, no icons

4. Apex Status widget — StatusBadge + one line of text in textSecondary

5. Activity Snapshot — last 3 ActivityFeedEntry components, no header

6. Primary action button — PrimaryButton, full width, contextual label

7. Live/Simulation toggle — small, right-aligned, textCaption, never prominent

States: Loading — show skeleton placeholders, not spinners. Empty — no trades yet, show "Apex is monitoring."

Quiet Confidence: No colour fills on the portfolio value. No trend arrows. Numbers only.

## 3.4 Step 3 — Prompt the Agent Precisely

The quality of the agent's UI output is directly proportional to the precision of the prompt. A vague prompt produces a generic screen. A precise prompt produces a screen that reflects Quiet Confidence.

The prompt structure for every screen build:

Standard Screen Build Prompt Structure:

1. Reference the design system — "Use the QuantroApex design system. Colour tokens: [list]. Spacing tokens: [list]."

2. Reference the component library — "Use these existing components: [list relevant ones]."

3. Provide the screen spec — paste the full spec written in Step 2.

4. State the philosophy — "This screen follows the Quiet Confidence principle: calm, composed, no visual noise."

5. Specify what not to do — "No gradients, no heavy shadows, no animations beyond the defined motion tokens."

6. Request states — "Provide loading, empty, and error states for each data-dependent element."

## 3.5 Step 4 — Consistency Audits

Even with a design system, the agent can drift over multiple screens. Two scheduled consistency audits catch this before it compounds.

| Audit | When | What to Check |
| --- | --- | --- |
| Mid-build audit | End of Sprint 6 | Spacing consistency across all built screens, colour token usage, component reuse vs custom builds, typography scale adherence |
| Pre-launch audit | Sprint 10 | Full Quiet Confidence review — all five principles applied to every screen, notification copy tone, activity feed entry language, error state messaging |

For each audit, walk through every screen on a physical device — not the simulator. Real devices reveal spacing issues, touch target sizes, and readability problems that simulators hide.

## 3.6 Experience Level Design Variants

Three experience levels produce UI variants across multiple screens. The design system handles this through a theme layer — the same components, different density settings applied at the app level based on user preference.

| Setting | Newcomer | Intermediate | Professional |
| --- | --- | --- | --- |
| Card padding | space4 (24px) | space3 (16px) | space3 (16px) |
| Information density | Low — one concept per card | Medium | High — data-rich |
| Tooltip visibility | Always visible | On tap | Hidden by default |
| AI reasoning detail | Full plain-English | Summarised | Technical + expandable |
| Metric display | Key 3 only | Standard set | Full suite |

In code, this is implemented as a single appDensity setting on the user profile — Newcomer, Intermediate, or Professional — that the design system components read and adapt to. The agent builds each component with this adaptability built in from the start.

## 3.7 The Quiet Confidence Visual Language — Quick Reference

The agent receives this as a standing reminder on every UI prompt.

| Never do this | Always do this instead |
| --- | --- |
| Red banner alerts for losses | Muted red text number only — the data speaks |
| Green celebration for profits | Green text number — composed, not excited |
| Gradient backgrounds | Flat white or flat colorSurface — clean |
| Heavy drop shadows on cards | Subtle 1px border, 2px shadow max |
| Full-screen loading spinners | Skeleton placeholders that match the layout |
| Pop-up notifications within app | Inline status updates in the activity feed |
| Decorative icons or illustrations | Functional icons only, from Material Symbols |
| Bold colour for simulation mode | Subtle muted badge — present, never alarming |
| Aggressive CTAs — "Start NOW!" | Calm single-word or short-phrase buttons |
| Multiple competing actions per screen | One primary action, supporting actions below |

# 4. MVP Scope

## 4.1 MVP Includes

- Flutter mobile application — iOS and Android

- Full onboarding — newcomer (9 steps) and professional (4 steps) paths

- Risk Vault — all parameters, emergency stop

- Strategy Marketplace — 10 curated strategies, recommendation engine

- Alpaca integration — stocks trading, paper and live

- Strategy-based execution engine — no self-learning yet

- Simulation (paper trading) mode — permanent, always available

- Home Dashboard — real-time portfolio and Apex status

- Apex Agent screen — activity feed, strategy display, phase indicator

- Performance screen — equity curve, key metrics, full trade history

- Advisory Mode — basic signal cards with plain-English reasoning

- Notification system — digests, milestones, loss threshold alerts

- Experience level system — Newcomer, Intermediate, Professional

- Node.js API backend, PostgreSQL database

## 4.2 Deferred to V2+

- Self-learning AI — Personal Agent and Global Brain (V2)

- Python AI services and Kafka pipeline (V2)

- Redis real-time caching layer (V2)

- Crypto and forex integrations — Binance, Coinbase, OANDA (V3)

- Reinforcement learning training loop (V3)

- Autonomous phase — AI developing its own strategies (V4)

- Web platform — Next.js (post-MVP)

# 5. Sprint Overview

| Sprint | Focus | Key Deliverable | Week |
| --- | --- | --- | --- |
| 0 | Project Setup + Design System | Stack running, design system document complete | Pre-sprint (2–3 days) |
| 1 | Auth & User Foundation | Signup, login, user profile working | Week 1 |
| 2 | Onboarding Flow | Both onboarding paths complete end-to-end | Week 2 |
| 3 | Risk Vault | All parameters, emergency stop functional | Week 3 |
| 4 | Strategy Marketplace | Browse, filter, select strategies | Week 4 |
| 5 | Alpaca Integration & Execution | Live order placed in Alpaca sandbox | Week 5 |
| 6 | Simulation Mode | Paper trading live, toggle functional | Week 6 |
| 7 | Dashboard & Activity Feed | Real-time dashboard, WebSocket feed live | Week 7 |
| 8 | Performance & Analytics | Equity curve, metrics, trade history | Week 8 |
| 9 | Notifications & Advisory | Push notifications and advisory feed live | Week 9 |
| 10 | Testing, Polish & Beta Launch | App store submitted, 500 beta users ready | Weeks 10–11 |

# 6. Sprint Details

## Sprint 0 — Project Setup & Design System

| Sprint 0 — Project Setup & Design System Goal: Full stack running locally. Design system document complete. | Pre-Sprint · 2–3 Days |
| --- | --- |

Sprint 0 now carries additional weight — it produces both the technical foundation and the design system document that governs every UI decision for the rest of the build. Completing both before Sprint 1 means the agent has everything it needs to produce consistent, intentional screens from day one.

AI Agent Tasks:

- Generate Flutter project scaffold — navigation, base theme file with all design tokens

- Generate Node.js project scaffold — folder structure, middleware, error handling

- Generate PostgreSQL schema — all tables and migrations

- Generate GitHub Actions CI/CD workflow files

- Generate component library stubs — all core components with token references

Founder Tasks:

- AWS infrastructure provisioned — staging and production

- Alpaca sandbox account and API credentials configured

- Environment variable management set up

- Git repository and branching strategy initialised

- Design System Document written — colours, typography, spacing, components, motion, Quiet Confidence quick reference

- Screen specs written for Sprints 1 and 2 — ready before Sprint 1 starts

Exit Criteria:

Full stack runs locally. CI/CD deploys to staging on push. Design System Document complete and committed to repository. Component library stubs generated and token-referenced.

## Sprint 1 — Authentication & User Foundation

| Sprint 1 — Auth & User Foundation Goal: A real user can sign up, log in, and reach the app home screen. | Week 1 |
| --- | --- |

AI Agent Tasks:

- Generate auth API endpoints — register, login, refresh, logout, password reset

- Generate JWT middleware for route protection

- Generate Flutter auth screens using design system tokens and component library

- Generate secure token storage — Flutter Secure Storage

- Generate user model and database migration

Founder Review:

- Validate JWT implementation — expiry, refresh logic, invalidation on logout

- Verify password hashing — bcrypt, no plain-text storage

- Design check — all screens use correct tokens, no hardcoded values

- Test auth flows end-to-end on physical device

Exit Criteria:

User registers, receives JWT, logs in, reaches home shell. Token refresh works silently. All screens match design system.

## Sprint 2 — Onboarding Flow

| Sprint 2 — Onboarding Flow Goal: Both onboarding paths complete end-to-end. | Week 2 |
| --- | --- |

Screen Specs Required Before Sprint:

- All 9 newcomer onboarding screens — written by founder, referenced by agent

- All 4 express setup screens

AI Agent Tasks:

- Generate all onboarding screens from specs, using design system throughout

- Generate onboarding state management — local and API sync

- Generate risk profile quiz logic

- Generate backend endpoints — experience level, risk profile, onboarding state, data consent

Founder Review:

- Read every line of onboarding copy — Quiet Confidence tone verified on each screen

- Design check — spacing, typography, component usage consistent with system

- Validate onboarding resume logic — mid-flow exit restarts at correct step

- Test both paths on iOS and Android physical devices

Exit Criteria:

Both paths complete end-to-end. Risk profile saved. Onboarding never shown again post-completion. All copy reviewed for calm, honest tone.

## Sprint 3 — Risk Vault

| Sprint 3 — Risk Vault Goal: All risk parameters enforced server-side. Emergency stop works. | Week 3 |
| --- | --- |

AI Agent Tasks:

- Generate Risk Vault CRUD endpoints

- Generate risk enforcement middleware

- Generate emergency stop endpoint and halt logic

- Generate Risk Vault and Settings Flutter screens from specs and design system

Founder Review — Critical:

- Manually test every risk enforcement edge case — this protects real money

- Verify emergency stop halts all execution with no pending orders left

- Confirm asset class toggles block at API layer, not UI layer only

- Design check — Risk Vault screen feels serious and precise, not alarming

Exit Criteria:

Risk Vault parameters enforced server-side on every trade request. Emergency stop instant. Every edge case tested manually by founder.

## Sprint 4 — Strategy Marketplace

| Sprint 4 — Strategy Marketplace Goal: Users browse, understand, and select a starting strategy. | Week 4 |
| --- | --- |

AI Agent Tasks:

- Generate strategy model, migrations, seed data structure

- Generate strategy API endpoints — list, filter, recommended, detail, selection

- Generate Strategy Marketplace screens from specs and design system

- Generate strategy card and detail bottom sheet components

Founder Tasks:

- Write all 10 strategy descriptions personally — plain English, Quiet Confidence tone

- Define backtested performance data for each strategy

- Validate recommendation algorithm — correct strategies surface for each risk profile

- Design check — strategy cards are informative, not sales-y

Exit Criteria:

User browses all strategies, views risk-based recommendations, selects one. Selection persists. All strategy copy written in plain English by founder.

## Sprint 5 — Alpaca Integration & Execution Engine

| Sprint 5 — Alpaca Integration & Execution Goal: System places real orders in Alpaca sandbox. | Week 5 |
| --- | --- |

AI Agent Tasks:

- Generate Alpaca API client — REST and WebSocket

- Generate unified broker interface layer

- Generate order placement, modification, cancellation logic

- Generate position tracker and trade logger

- Generate strategy rule interpreter

Founder Review — Critical:

- Manually test every order type in sandbox — market, limit, edge cases

- Verify broker interface truly abstracts Alpaca — no leaking specifics

- Validate trade logger captures all fields correctly

- Test Start and Stop Apex — clean state transitions, no orphaned orders

Exit Criteria:

System places a real order in Alpaca sandbox, logs it, tracks the position, reflects in portfolio.

## Sprint 6 — Simulation Mode

| Sprint 6 — Simulation Mode Goal: Full paper trading live. Mid-build design consistency audit complete. | Week 6 |
| --- | --- |

AI Agent Tasks:

- Generate simulation execution engine — mirrors live, is_simulated flag

- Generate real market data feed for simulation

- Generate simulated slippage and spread application

- Generate separate simulated portfolio tracking

- Generate Live/Simulation toggle component from design system

Founder Tasks:

- Verify simulation prices match live market — no unrealistic paper trading gap

- Confirm live and simulated portfolios fully isolated

- Design check — simulation indicator subtle and calm, not a warning

- MID-BUILD DESIGN AUDIT — walk through all screens built to date on physical device:

- Spacing consistent across all screens — check against 8-point grid

- Colour tokens used throughout — no hardcoded hex values

- Components reused correctly — no rebuilt variants that should use the library

- Typography scale consistent — no custom font sizes outside the scale

- Fix any inconsistencies before continuing

Exit Criteria:

Simulation fully functional. Toggle works. Mid-build audit complete and all inconsistencies resolved.

## Sprint 7 — Dashboard & Activity Feed

| Sprint 7 — Dashboard & Activity Feed Goal: Real-time dashboard live. Activity feed updates via WebSocket. | Week 7 |
| --- | --- |

AI Agent Tasks:

- Generate portfolio summary, Apex status, activity feed API endpoints

- Generate WebSocket server — real-time trade event push

- Generate plain-English trade description generator

- Generate Home Dashboard and Apex Agent screens from specs and design system

- Generate Activity Feed and Last Trade Card components

Founder Review:

- Read every generated activity feed entry — plain English audit, no jargon whatsoever

- Test WebSocket — reconnects cleanly, no duplicate events on reconnect

- Confirm dashboard data accuracy against database state

- Design check — dashboard feels calm, not like a trading floor

Exit Criteria:

Dashboard shows live data. Feed updates in real time. Every entry plain English. WebSocket reconnects cleanly.

## Sprint 8 — Performance Screen & Analytics

| Sprint 8 — Performance & Analytics Goal: Full trade history, metrics, and equity curve live. | Week 8 |
| --- | --- |

AI Agent Tasks:

- Generate performance summary, equity curve, trade history, trade detail endpoints

- Generate Performance screen from spec and design system

- Generate equity curve chart, metrics grid, trade history list, trade detail expansion

Founder Review:

- Manually verify all metric calculations — total return, win rate, averages

- Verify Simulation vs Live data isolation on all endpoints

- Test equity curve accuracy against actual trade log

- Design check — performance screen lets numbers speak, no motivational language

- Begin AI/ML Engineer search — do not wait until after beta

Exit Criteria:

Accurate metrics, correct equity curve, filterable trade history. All calculations manually verified.

## Sprint 9 — Notifications & Advisory Mode

| Sprint 9 — Notifications & Advisory Mode Goal: Notification system and advisory feed live. | Week 9 |
| --- | --- |

AI Agent Tasks:

- Generate Firebase Cloud Messaging integration

- Generate notification service, scheduled jobs, milestone detection

- Generate loss threshold monitor

- Generate notification preferences model and endpoints

- Generate advisory signal engine — basic momentum and trend signals

- Generate Advisory Feed screen and signal card components from design system

Founder Review:

- Read every notification message — calm framing verified on all alert types

- Test loss threshold alert fires correctly and respects opt-out immediately

- Review advisory signal quality — useful signals or noise

- Test push notifications on physical iOS and Android devices

- Design check — advisory feed is informative, not overwhelming

Exit Criteria:

Push notifications delivered at correct intervals. Loss alert fires and respects opt-out. Advisory feed live. All notification copy reviewed for calm tone.

## Sprint 10 — Testing, Polish & Beta Launch

| Sprint 10 — Testing, Polish & Beta Launch Goal: Stable, polished, 500 beta users ready to onboard. | Weeks 10–11 |
| --- | --- |

The only two-week sprint. For a financial product this time cannot be compressed. Testing and polish here determines whether users trust the product with real money.

AI Agent Tasks:

- Generate end-to-end test suite — full user journey coverage

- Generate load testing scripts — 500 concurrent users

- Generate any missing unit tests

Founder Tasks — Testing:

- Manual end-to-end run — every flow, every screen, on both iOS and Android

- Security audit — JWT handling, API exposure, input sanitisation, user data isolation

- Financial logic audit — execution engine, risk enforcement, portfolio calculations

- Load test — 500 concurrent users on API and WebSocket

Founder Tasks — Quiet Confidence Audit:

- Walk through every screen on physical device — five principles applied to each

- Notification copy final review — every message calm and clear

- Activity feed entry final review — every entry plain English, no jargon

- Error state review — all errors informative, never alarming

- Simulation indicator review — subtle on every screen it appears

- Typography check — no text outside the scale, no inconsistent weights

- Spacing check — 8-point grid honoured throughout

Founder Tasks — Launch:

- App Store submission — screenshots, metadata, privacy policy, compliance

- Google Play submission — store listing, content rating, data safety form

- 500 beta invite codes generated

- Beta documentation — what to expect, how to give feedback, known limitations

- Sentry error tracking, uptime alerts, performance monitoring configured

Exit Criteria:

App passes App Store and Google Play review.

No critical bugs in any core user flow.

Security audit passed — no open vulnerabilities.

Quiet Confidence audit complete — all screens reviewed and approved.

500 beta invites ready to send.

All production monitoring active.

# 7. Post-MVP Release Roadmap

| Version | Focus | Timeline | New Capabilities |
| --- | --- | --- | --- |
| MVP | Core product + strategy execution | Weeks 1–11 | Flutter app, Alpaca, simulation, advisory |
| V2 | Intelligence layer | Weeks 18–30 | Python AI service, signal models, Redis, Personal Agent begins |
| V3 | Learning engine | Weeks 31–46 | RL loop, full Personal Agent, Kafka, crypto + forex |
| V4 | Full autonomy | Weeks 47–62 | Global Brain, Autonomous phase, circuit breaker, all brokers |

Weeks 12–17 are intentional breathing room between MVP beta and V2 — gather feedback, fix post-launch issues, finalise V2 scope from real data, complete AI/ML Engineer hire.

# 8. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| AI agent produces inconsistent UI across screens | Medium | Design system document referenced on every prompt. Mid-build audit at Sprint 6. Pre-launch audit at Sprint 10. |
| AI agent produces incorrect financial logic | Medium | Founder manually reviews all execution engine, risk enforcement, and portfolio calculation outputs. Never accept without verification. |
| Context switching causes drift from vision | Medium | Written daily log every day. Product blueprint and design system referenced before every sprint. |
| Sprint velocity slower than planned | Low | Sprint 10 has two-week buffer. Advisory Mode is lowest MVP priority and can be trimmed. |
| Alpaca API changes or downtime | Medium | Unified broker interface — swap integration without touching core logic. |
| Security vulnerability in auth or API | Low | Security audit Sprint 10. JWT validated by founder Sprint 1. |
| App Store rejection | Low | Financial app compliance researched Sprint 0. Privacy policy prepared before submission. |
| AI/ML Engineer hire takes too long | High | Search begins Sprint 6. Longest hiring timeline in the roadmap. Late start pushes V2. |

# 9. Summary

QuantroApex MVP — Solo Build at a Glance

Methodology: Agile / Scrum — 1-week sprints

Build Approach: Solo founder + AI coding agent

External Support: None — fully self-contained build

Total Sprints: 10 delivery sprints + Sprint 0

Total Duration: 11 weeks to beta launch

Beta Target: End of Week 11

Beta Users: 500 invited users

Primary Platform: Flutter mobile — iOS and Android

Backend: Node.js + PostgreSQL

Broker: Alpaca (stocks — paper and live)

AI in MVP: Strategy execution only — learning engine deferred to V2

Design Approach: Design system document + agent-built screens + two consistency audits

AI/ML Hire Search: Begins Sprint 6 — in place before V2 planning

— End of Document —

Quantro Software Labs  |  QuantroApex Development Plan v3.0  |  Confidential